## Consultancy
| PROCUREMENT PLAN 2022 - CONSULTANCY | N° of Consultant |  |  | Basic data | [5 empty] | Impementation |  | Duration
S/N | Description - Resource Persons Needed per Activity | International | Regional | N° of Days | Selection Method | Lump Sum or Time- Based | Estimated Budget USD | Estimated Budget UA | Prior/ Post Review | Plan vs. Actual | Start Date (of the Procurement Process) | End Date ( of the procurement process in line with Procurement deadline set up in the Code) | Total Duration of the Procurement process
List of Contract
1 | National Workshop on Enhacing AML/CFT Compliance by Designated Non-Financial Businesses & Professions and Non-Profit Organizations (Precious metal/mineral dealers) | 1 | 3 | 3 | ICS | Lump Sum | 17050 | 12278.6247 |  | PLAN |  |  | 1 week
Actual
2 | National Workshop on Preventing ML/TF through the Non-Profit Organizations (NPO/NGOs) for operators and managers of NPOs/NGOs | 1 | 2 | 3 | ICS | Lump Sum | 10730 | 7727.2518 |  | PLAN |  |  | 1 week
Actual
3 | Regional Meeting of Chief Compliance Officers of FIs, DNFBPs, and Competent Authorities on Emerging Money Laundering & Terrorist Financing Issues - Senegal | 3 | 4 | 1 | ICS | Lump Sum | 31404 | 22615.7143 |  | PLAN |  |  | 1 week
Actual
4 | Regional Virtual Training Workshop on Counter Proliferation Financing for Relevant National Competent Authorities - Senegal | 0 | 5 | 3 | ICS | Lump Sum | 10344 | 7449.2724 |  | PLAN |  |  | 1 week
Actual
5 | Regional Workshop (Hybrid) on ML/TF Risks from Virtual Currency and VASPs | 0 | 2 | 5 | ICS | Lump Sum | 4000 | 2880.6158 |  | PLAN |  |  | 1 week
Actual
6 | National Workshop on Combating the Financing of Terrorism and Cross-Border Cash Smuggling for LEA | 2 | 2 | 5 | ICS | Lump Sum | 14440 | 10399.0229 |  | PLAN |  |  | 1 week
Actual
7 | Development of a Guidance Handbook on Good Practices on CFT for NPOs | 0 | 3 | 1 | CQ | Lump Sum | 17944 | 12922.4423 |  | PLAN |  |  | 1 week
Actual
8 | GIABA Annual Typologies Exercise and workshop (Typologies workshop on the finalization of the study on Cyber crime in West Africa) | 2 | 0 | 3 | ICS | Lump Sum | 8020 | 5775.6346 |  | PLAN |  |  | 1 week
Actual
9 | Support for Inter-Ministerial Commitees and Follow up on National Strategies/Action plan development for MS | 0 | 3 | 3 | CQ | Lump Sum | 23130 | 16657.1606 |  | PLAN |  |  | 1 week
Actual
10 | National Workshop on Financial Crime Investigations for member States | 3 | 3 | 6 | CQ | Lump Sum | 19032 | 13705.9698 |  | PLAN |  |  | 1 week
Actual
11 | GIABA VIRTUAL SHARING SESSION ON APPLICATION OF FATF RECOMMENDATIONS AND THE GIABA PROCESS AND PROCEDURES | 0 | 9 | 5 | CQ | Lump Sum | 18000 | 12962.7709 |  | PLAN |  |  | 1 week
Actual
12 | Regional Hybrid Training Workshop on Asset Recovery for GIABA Member States (Anglophone and Francophone/Lusophone) | 4 | 4 | 4 | ICS | Lump Sum | 11200 | 8065.7241 |  | PLAN |  |  | 1 week
Actual
13 | Joint ECOWAS/Court of Justice/GIABA Regional Capacity building workshop on the Adjudication Economic and Financial Crimes cases for Judges | 3 | 3 | 3 | ICS | Lump Sum | 14160 | 10197.3798 |  | PLAN |  |  | 1 week
Actual
14 | GIABA Assessors Training and MER Report Writing | 2 | 2 | 5 | ICS | Lump Sum | 14336 | 10324.1269 |  | PLAN |  |  | 1 week
Actual
15 | GIABA Regional Training on FATF Standards and Methodology | 2 | 2 | 5 | ICS | Lump Sum | 14336 | 10324.1269 |  | PLAN |  |  | 1 week
Actual
16 | Mutual Evaluation of Guinea (On-site visit and Face-to-Face Meeting) | 3* | 5 | 5*/ 7 | ICS | Lump Sum | 20000 | 14403.0788 |  | PLAN |  |  | 1 week
Actual
17 | Mutual Evaluation of Comoros (On-site visit and Face-to-Face Meeting) | 3* | 5 | 5*/ 7 | ICS | Lump Sum | 20000 | 14403.0788 |  | PLAN |  |  | 1 week
Actual
18 | Mutual Evaluation of Sao Tome e Principe (On-site visit and Face-to-Face Meeting) | 3* | 5 | 5*/ 7 | ICS | Lump Sum | 20000 | 14403.0788 |  | PLAN |  |  | 1 week
Actual
19 | National Mutual Evaluation Pre-Assessment Training for MS and Preparation for ME (Guinea) |  | 1 | 4 | ICS | Lump Sum | 1600 | 1152.2463 |  | PLAN |  |  | 1 week
Actual
20 | Technical and Financial Support to member States assessed to address the ME strategic deficiencies identified in their Mutual Evaluation Report |  | 1 | 4 | CQ | Lump Sum | 60000 | 43209.2364 |  | PLAN |  |  | 1 week
Actual
21 | Mutual Evaluation of The Gambia - (Face-to-Face Meeting) (Completion) |  | 1 | 7 | ICS | Lump Sum | 11004 | 7924.574 |  | PLAN |  |  | 1 week
Actual
22 | Mutual Evaluation of Liberia - (On-site visit and Face-to-Face Meeting) |  | 6 | 20 | ICS | Lump Sum | 36000 | 25925.5418 |  | PLAN |  |  | 1 week
Actual
23 | Mutual Evaluation of Côte d'Ivoire (On-site visit and Face-to-Face Meeting) |  | 3* | 7 | ICS | Lump Sum | 8400 | 6049.2931 |  | PLAN |  |  | 1 week
Actual
24 | National AML/CFT Media Outreach Activities |  | 2 | 1 | ICS | Lump Sum | 2372 | 1708.2051 |  | PLAN |  |  | 1 week
Actual
25 | Annual Ambassadors Briefing |  | 2 | 1 | ICS | Lump Sum | 2372 | 1708.2051 |  | PLAN |  |  | 1 week
Actual
26 | Regional Sensitization Workshop for CSOs on AML/CFT requirements | 1 | 2 | 3 | ICS | Lump Sum | 7006 | 5045.3985 |  | PLAN |  |  | 1 week
Actual
27 | 2 Open House for Youths / National AML/CFT Awareness Raising Road Show for the General Public |  | 4 | 2 | ICS | Lump Sum | 3200 | 2304.4926 |  | PLAN |  |  | 1 week
Actual
28 | Regional Training for Journalists on Investigative Reporting of Economic Crimes in W/A | 1 | 2 | 5 | ICS | Lump Sum | 7530 | 5422.7592 |  | PLAN |  |  | 1 week
Actual
29 | Annual World Press Conference/Presentation of 2021 Annual Report |  | 1 | 3 | ICS | Lump Sum | 1186 | 854.1026 |  | PLAN |  |  | 1 week
Actual
31 | National Sensitization Seminar for Religious Leaders and Institutions on AML/CFT |  | 3 | 4 | ICS | Lump Sum | 8688 | 6256.6974 |  | PLAN |  |  | 1 week
Actual
| TOTAL | [5 empty] | 437484 | 315055.8263
| NA: Not Applicable |  |  |  | Exchange Rate | NA: Not Applicable |  |  | Exchange Rate
| CQ: Consultant Qualifications - (2 months) |  |  |  | 1UA = 1.438772 | CQ: Consultant Qualifications - (2 months) |  |  | 1UA =
| ICS: Selection of Individual Consultant (2 months) |  |  |  |  | ICS: Selection of Individual Consultant (2 months)
| QCBS: Quality Cost Based Selection (4 months) |  |  |  |  | QCBS: Quality Cost Based Selection (4 months) |  |  |  | *inclusive of reviewers
| DC: Direct Contracting (2 months) |  |  |  |  | DC: Direct Contracting (1 month)
| LCS: Least Cost Selection (4 months) |  |  |  |  | LCS: Least Cost Selection (4 months)
| CP: Call for Proposals |  |  |  |  | QBS: Quality Based Selection (4 months)

## Goods
|  | PROCUREMENT PLAN 2022 - GOODS | Basic data | [7 empty] | Implementation |  | Duration
S/N | N° of Days | Description | Item | Lot No. | Estimated Buget USD | Estimated Budget UA | Procurement Method | Pre/Post Qualification | Prior/ Post Review | Plan vs. Actual | Start Date (of the Procurement Process)* | End Date ( of the procurement process in line with Procurement deadline set up in the Code) | Total Duration of the Procurement process
List of Contracts
Plan-Actual
1 | 3 | National Workshop on Enhacing AML/CFT Compliance by Designated Non-Financial Businesses & Professions and Non-Profit Organizations (Precious metal/mineral dealers) - Sierra Leone | Conference Hall | 1 | 3300 | 2376.508 | Post Qualification | Prior | Plan
Actual
|  |  | Secretariat Room | 1 | 2100 | 1512.3233 | Post Qualification | Prior | Plan
Actual
|  |  | Tea Break | 60 | 7200 | 5185.1084 | Post Qualification | Prior | Plan
Actual
|  |  | Photocopier | 1 | 900 | 648.1385 | Post Qualification | Prior | Plan
Actual
|  |  | Computers | 1 | 450 | 324.0693 | Post Qualification | Prior | Plan
Actual
|  |  | Printer | 1 |  |  | Post Qualification | Prior | Plan
Actual
|  |  | Publicity Materials (USB, Keys, Notepads, Pens,Banner) | 100 | 5000 | 3600.7697 | Post Qualification | Prior | Plan
Actual
|  |  | Internet connection | 1 | 200 | 144.0308 | Post Qualification | Prior | Plan
Actual
|  |  | Interpretation Equipment | 0 |  |  | Post Qualification | Prior | Plan
Actual
|  |  | Bus | 0 |  |  | Post Qualification | Prior | Plan
Actual
|  |  | Car | 0 |  |  | Post Qualification | Prior | Plan
Actual
2 | 3 | National Workshop on Preventing ML/TF through the Non-Profit Organizations (NPO/NGOs) for operators and managers of NPOs/NGOs - Cabo Verde | Conference Hall | 1 | 4500 | 3240.6927 | Post Qualification | Prior | Plan
Actual
|  |  | Secretariat Room | 1 | 2000 | 1440.3079 | Post Qualification | Prior | Plan
Actual
|  |  | Tea Break | 80 | 7800 | 5617.2007 | Post Qualification | Prior
|  |  | Photocopier | 1 | 900 | 648.1385 | Post Qualification | Prior | Plan
Actual
|  |  | Computers | 1 | 450 | 324.0693 | Post Qualification | Prior | Plan
Actual
|  |  | Printer | 1 |  |  | Post Qualification | Prior | Plan
Actual
|  |  | Publicity Materials (USB, Keys, Notepads, Pens,Banner) | 120 | 6000 | 4320.9236 | Post Qualification | Prior | Plan
Actual
|  |  | Internet connection | 1 | 200 | 144.0308 | Post Qualification | Prior | Plan
Actual
|  |  | Interpretation Equipment | 0 |  |  | Post Qualification | Prior | Plan
Actual
|  |  | Bus | 0 |  |  | Post Qualification | Prior | Plan
Actual
|  |  | Car | 0 |  |  | Post Qualification | Prior | Plan
Actual
3 | 5 | Regional Hybrd Meeting of Chief Compliance Officers of FIs, DNFBPs, and Competent Authorities on Emerging Money Laundering & Terrorist Financing Issues | Conference Hall | 1 | 10000 | 7201.5394 | Post Qualification | Prior | Plan
Actual
|  |  | Secretariat Room | 1 | 2500 | 1800.3849 | Post Qualification | Prior | Plan
Actual
|  |  | Tea Break | 70 | 22400 | 16131.4483 | Post Qualification | Prior | Plan
Actual
|  |  | Photocopier | 1 | 1500 | 1080.2309 | Post Qualification | Prior | Plan
Actual
|  |  | Computers | 1 | 750 | 540.1155 | Post Qualification | Prior | Plan
Actual
|  |  | Printer | 1 | 750 | 540.1155 | Post Qualification | Prior | Plan
Actual
|  |  | Publicity Materials (USB, Keys, Notepads, Pens,Banner) | 180 | 45000 | 32406.9273 | Post Qualification | Prior | Plan
Actual
|  |  | Internet connection | 1 | 1000 | 720.1539 | Post Qualification | Prior | Plan
Actual
|  |  | Interpretation Equipment | 1 | 2000 | 1440.3079 | Post Qualification | Prior | Plan
Actual
|  |  | Bus | 3 | 2250 | 1620.3464 | Post Qualification | Prior | Plan
Actual
|  |  | Eworking logistics Allocations, Internet Reinforcements | 50 | 25025 | 18021.8524 | Post Qualification | Prior | Plan
Actual
4 | 3 | Regional Virtual Training Workshop on Counter Proliferation Financing for Relevant National Competent Authorities | Conference Hall | 1 | 0 | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Secretariat Room | 1 | 0 | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Tea Break | 55 | 0 | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Photocopier | 1 | 0 | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Computers | 1 | 0 | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Printer | 1 | 0 | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Publicity Materials (USB, Keys, Notepads, Pens,Banner) | 55 | 0 | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Internet Connection | 30 | 2250 | 1620.3464 | Post Qualification | Prior | Plan
Actual
|  |  | Interpretation Equipment | 1 | 0 | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Bus | 2 | 0 | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Car | 0 |  |  | Post Qualification | Prior | Plan
Actual
5 | 5 | Regional Workshop (Hybrid) on ML/TF Risks from Virtual Currency and VASPs | Conference Hall | 1 | 3000 | 2160.4618 | Post Qualification | Prior | Plan
Actual
|  |  | Secretariat Room | 1 | 1500 | 1080.2309 | Post Qualification | Prior | Plan
Actual
|  |  | Tea Break | 55 | 16500 | 11882.54 | Post Qualification | Prior | Plan
Actual
|  |  | Photocopier | 1 | 1000 | 720.1539 | Post Qualification | Prior | Plan
Actual
|  |  | Computers | 1 | 250 | 180.0385 | Post Qualification | Prior | Plan
Actual
|  |  | Printer | 1 | 250 | 180.0385 | Post Qualification | Prior | Plan
Actual
|  |  | Publicity Materials (USB, Keys, Notepads, Pens,Banner) | 56 | 2200 | 1584.3387 | Post Qualification | Prior | Plan
Actual
|  |  | Internet Connection | 1 | 500 | 360.077 | Post Qualification | Prior | Plan
Actual
|  |  | Interpretation Equipment | 0 | 1000 | 720.1539 | Post Qualification | Prior | Plan
Actual
|  |  | Bus | 4 | 8000 | 5761.2315 | Post Qualification | Prior | Plan
Actual
|  |  | Car | 3 | 2250 | 1620.3464 | Post Qualification | Prior | Plan
Actual
6 | 3 | National Workshop on Combating the Financing of Terrorism and Cross-Border Cash Smuggling for LEA | Conference Hall | 1 | 6300 | 4536.9698 | Post Qualification | Prior | Plan
Actual
|  |  | Secretariat Room | 1 | 2100 | 1512.3233 | Post Qualification | Prior | Plan
[6 empty] | 0 |  |  | Actual
|  |  | Tea Break | 67 |  | 11457 | Post Qualification | Prior | Plan
Actual
|  |  | Photocopier | 1 |  | 900 | Post Qualification | Prior | Plan
Actual
|  |  | Computers | 1 |  | 450 | Post Qualification | Prior | Plan
Actual
|  |  | Printer | 0 |  | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Publicity Materials (USB, Keys, Notepads, Pens,Banner) | 70 | 3500 | 2520.5388 | Post Qualification | Prior | Plan
Actual
|  |  | Internet connection | 1 | 200 | 144.0308 | Post Qualification | Prior | Plan
Actual
|  |  | Interpretation Equipment | 0 |  | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Bus | 0 |  | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Car | 1 | 150 | 108.0231 | Post Qualification | Prior | Plan
Actual
7 | 2 | Development of a Guidance Handbook on Good Practices on CFT for NPOs | Conference Hall | 1 | 1200 | 864.1847 | Post Qualification | Prior | Plan
Actual
|  |  | Secretariat Room | 1 | 402 | 289.5019 | Post Qualification | Prior | Plan
Actual
|  |  | Tea Break | 76 | 13680 | 9851.7059 | Post Qualification | Prior | Plan
Actual
|  |  | Photocopier | 1 | 400 | 288.0616 | Post Qualification | Prior | Plan
Actual
|  |  | Computers/printer | 1 | 170.12 | 122.5126 | Post Qualification | Prior | Plan
Actual
|  |  | Printer | 1 | 0 | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Publicity Materials (USB, Keys, Notepads, Pens, Banner) | 1 | 400 | 288.0616 | Post Qualification | Prior | Plan
Actual
|  |  | Internet connection | 2 | 400 | 288.0616 | Post Qualification | Prior | Plan
Actual
|  |  | Interpretation Equipment | 1 | 1000 | 720.1539 | Post Qualification | Prior | Plan
Actual
|  |  | Bus | 1 | 1550 | 1116.2386 | Post Qualification | Prior | Plan
Actual
|  |  | Car | 1 | 0 | 0 | Post Qualification | Prior | Plan
Actual
8 | 2 | GIABA RTMG Meetings (Plenary) | Conference Hall | 1 | 1200 | 864.1847 | Post Qualification | Prior | Plan
Actual
|  |  | Secretariat Room | 1 | 600 | 432.0924 | Post Qualification | Prior | Plan
Actual
|  |  | Tea Break | 31 | 3100 | 2232.4772 | Post Qualification | Prior | Plan
Actual
|  |  | Photocopier | 1 | 400 | 288.0616 | Post Qualification | Prior | Plan
Actual
|  |  | Computers | 1 | 100 | 72.0154 | Post Qualification | Prior | Plan
Actual
|  |  | Printer | 1 | 100 | 72.0154 | Post Qualification | Prior | Plan
Actual
|  |  | Publicity Materials (USB, Keys, Notepads, Pens) | 0 | 0 | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Internet Connection | 5 | 1000 | 720.1539 | Post Qualification | Prior | Plan
Actual
|  |  | Interpretation Equipment | 1 | 2000 | 1440.3079 | Post Qualification | Prior | Plan
Actual
|  |  | Bus | 2 | 0 | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Car | 2 | 3000 | 2160.4618 | Post Qualification | Prior | Plan
Actual
9 | 5 | Ongoing Follow Up / Updates on Terrorist Financing | Conference Hall | 1 | 9000 | 6481.3855 | Post Qualification | Prior | Plan
Actual
|  |  | Secretariat Room | 1 | 0 | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Tea Break | 30 | 9000 | 6481.3855 | Post Qualification | Prior | Plan
Actual
|  |  | Photocopier | 1 | 0 | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Computers | 1 | 0 | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Printer | 1 | 500 | 360.077 | Post Qualification | Prior | Plan
Actual
|  |  | Publicity Materials (USB, Keys, Notepads, Pens, Banners) | 1 | 1000 | 720.1539 | Post Qualification | Prior | Plan
Actual
|  |  | Transport for equipment | 1 | 2500 | 1800.3849 | Post Qualification | Prior | Plan
Actual
|  |  | Interpretation Equipment | 1 | 0 | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Bus | 2 | 0 | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Car | 0 |  |  | Post Qualification | Prior | Plan
Actual
10 | 5 | Stakeholders workshop on the study on ML Risks & Vulnerabilities of Casinos & the Gaming sector in WA | Conference Hall | 1 | 3000 | 2160.4618 | Post Qualification | Prior | Plan
Actual
|  |  | Secretariat Room | 1 | 1500 | 1080.2309 | Post Qualification | Prior | Plan
Actual
|  |  | Tea Break | 45 | 13500 | 9722.0782 | Post Qualification | Prior | Plan
Actual
|  |  | Photocopier | 1 | 1000 | 720.1539 | Post Qualification | Prior | Plan
Actual
|  |  | Computers | 1 | 250 | 180.0385 | Post Qualification | Prior | Plan
Actual
|  |  | Printer | 1 | 250 | 180.0385 | Post Qualification | Prior | Plan
Actual
|  |  | Publicity Materials (USB, Keys, Notepads, Pens,Banners) | 0 |  | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Internet Connection | 1 | 500 | 360.077 | Post Qualification | Prior | Plan
Actual
|  |  | Interpretation Equipment | 1 | 1000 | 720.1539 | Post Qualification | Prior | Plan
Actual
|  |  | Bus | 0 |  | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Car | 4 | 8000 | 5761.2315 | Post Qualification | Prior | Plan
Actual
11 | 5 | GIABA Annual Typologies Exercise and workshop (Typologies workshop on the finalization of the study on Cyber crime in West Africa) | Conference Hall | 1 | 3000 | 2160.4618 | Post Qualification | Prior | Plan
Actual
|  |  | Secretariat Room | 1 | 1500 | 1080.2309 | Post Qualification | Prior | Plan
Actual
|  |  | Tea Break | 75 | 18750 | 13502.8864 | Post Qualification | Prior | Plan
Actual
|  |  | Photocopier | 1 | 1000 | 720.1539 | Post Qualification | Prior | Plan
Actual
|  |  | Computers | 1 | 250 | 180.0385 | Post Qualification | Prior | Plan
Actual
|  |  | Printer | 1 | 250 | 180.0385 | Post Qualification | Prior | Plan
Actual
|  |  | Publicity Materials (USB, Keys, Notepads, Pens) | 54 | 2300 | 1656.3541 | Post Qualification | Prior | Plan
Actual
|  |  | Internet Connection | 5 | 2500 | 1800.3849 | Post Qualification | Prior | Plan
Actual
|  |  | Interpretation Equipment | 1 | 5000 | 3600.7697 | Post Qualification | Prior | Plan
Actual
|  |  | Bus | 1 | 2000 | 1440.3079 | Post Qualification | Prior | Plan
Actual
|  |  | Car | 2 | 1500 | 1080.2309 | Post Qualification | Prior | Plan
Actual
12 | 4 | National sharing sessions on 2 research outcomes in WA(Casino & Assessment of the ML/TF Investigation and Prosecution Challenges) | Conference Hall | 6 | 19200 | 13826.9557 | Post Qualification | Prior | Plan
Actual
|  |  | Secretariat Room | 1 | 0 | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Tea Break | 30 | 43200 | 31110.6502 | Post Qualification | Prior | Plan
Actual
|  |  | Photocopier | 6 | 3600 | 2592.5542 | Post Qualification | Prior | Plan
Actual
|  |  | Projectors | 6 | 3600 | 2592.5542 | Post Qualification | Prior | Plan
Actual
|  |  | Printer | 6 | 3600 | 2592.5542 | Post Qualification | Prior | Plan
Actual
|  |  | Publicity Materials (USB, Keys, Notepads, Pens, Banners) | 6 | 600 | 432.0924 | Post Qualification | Prior | Plan
Actual
|  |  | Internet Connection | 6 | 4800 | 3456.7389 | Post Qualification | Prior | Plan
Actual
|  |  | Interpretation Equipment | 3 | 12000 | 8641.8473 | Post Qualification | Prior | Plan
Actual
|  |  | Bus | 1 | 0 | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Car | 6 | 3600 | 2592.5542 | Post Qualification | Prior | Plan
Actual
13 | 9 | Support for Inter-Ministerial Commitees and Follow up on National Strategies/Action plan development for MS | Conference Hall | 2 | 10200 | 7345.5702 | Post Qualification | Prior | Plan
Actual
|  |  | Secretariat Room | 2 | 6000 | 4320.9236 | Post Qualification | Prior | Plan
Actual
|  |  | Tea Break | 230 | 82800 | 59628.7462 | Post Qualification | Prior | Plan
Actual
|  |  | Photocopier Computer Printer | 1 | 5850 | 4212.9005 | Post Qualification | Prior | Plan
Actual
|  |  | Telephone services | 5 | 1800 | 1296.2771 | Post Qualification | Prior | Plan
Actual
|  |  | Photograph | 5 | 1000 | 720.1539 | Post Qualification | Prior | Plan
Actual
|  |  | Publicity Materials (USB, Keys, Notepads, Pens) | 0 |  |  | Post Qualification | Prior | Plan
Actual
|  |  | Banners | 0 |  |  | Post Qualification | Prior | Plan
Actual
|  |  | Interpretation Equipment | 1 | 4000 | 2880.6158 | Post Qualification | Prior | Plan
Actual
|  |  | Bus | 1 | 1800 | 1296.2771 | Post Qualification | Prior | Plan
Actual
|  |  | Car | 0 |  |  | Post Qualification | Prior | Plan
Actual
14 | 5 | Follow Up on GIABA CFT Strategy and Action Plan Implementation by MS | Conference Hall | 1 | 9000 | 6481.3855 | Post Qualification | Prior | Plan
Actual
|  |  | Secretariat Room | 1 | 0 | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Tea Break | 30 | 9000 | 6481.3855 | Post Qualification | Prior | Plan
Actual
|  |  | Photocopier | 1 | 0 | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Computers | 1 | 0 | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Printer | 1 | 500 | 360.077 | Post Qualification | Prior | Plan
Actual
|  |  | Publicity Materials (USB, Keys, Notepads, Pens,Banner) | 1 | 1000 | 720.1539 | Post Qualification | Prior | Plan
Actual
|  |  | Transport for Equipment | 5 | 500 | 360.077 | Post Qualification | Prior | Plan
Actual
|  |  | Interpretation Equipment | 1 | 0 | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Bus | 1 | 0 | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Car | 0 |  |  | Post Qualification | Prior | Plan
Actual
15 | 5 | Computer Based Training/eLearning Training and Support | Conference Hall | 1 | 9000 | 6481.3855 | Post Qualification | Prior | Plan
Actual
|  |  | Secretariat Room | 1 | 0 | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Tea Break | 30 | 9000 | 6481.3855 | Post Qualification | Prior | Plan
Actual
|  |  | Photocopier | 1 | 0 | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Computers | 1 | 0 | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Printer | 1 | 500 | 360.077 | Post Qualification | Prior | Plan
Actual
|  |  | Publicity Materials (USB, Keys, Notepads, Pens, Banners) | 1 | 1000 | 720.1539 | Post Qualification | Prior | Plan
Actual
|  |  | Transport for equipment | 1 | 2500 | 1800.3849 | Post Qualification | Prior | Plan
Actual
|  |  | Interpretation Equipment | 1 | 0 | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Bus | 2 | 0 | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Car | 0 |  |  | Post Qualification | Prior | Plan
Actual
16 | 4 | National Workshop on Financial Crime Investigations for member States | Conference Hall | 1 | 7200 | 5185.1084 | Post Qualification | Prior | Plan
Actual
|  |  | Secretariat Room | 1 | 3000 | 2160.4618 | Post Qualification | Prior | Plan
Actual
|  |  | Tea Break | 59 | 21240 | 15296.0697 | Post Qualification | Prior | Plan
Actual
|  |  | Photocopier | 1 | 1200 | 864.1847 | Post Qualification | Prior | Plan
Actual
|  |  | Computers/Printer | 1 | 2400 | 1728.3695 | Post Qualification | Prior | Plan
Actual
|  |  | Internet Connection | 1 | 200 | 144.0308 | Post Qualification | Prior | Plan
Actual
|  |  | Publicity Materials (USB, Keys, Notepads, Pens, BAnner) | 59 | 2950 |  | Post Qualification | Prior | Plan
Actual
|  |  | Banners | 0 |  |  | Post Qualification | Prior | Plan
Actual
|  |  | Interpretation Equipment | 0 |  |  | Post Qualification | Prior | Plan
Actual
|  |  | Bus | 0 |  |  | Post Qualification | Prior | Plan
Actual
|  |  | Car | 3 | 0 | 0 | Post Qualification | Prior | Plan
Actual
17 | 20 | Mutual Evaluation of Guinea (On-site visit and Face-to-Face Meeting) | Conference Hall | 0 |  |  | Post Qualification | Prior | Plan
Actual
|  |  | Secretariat Room | 1 | 7200 | 5185.1084 | Post Qualification | Prior | Plan
Actual
|  |  | Tea Break | 10 | 3000 | 2160.4618 | Post Qualification | Prior | Plan
Actual
|  |  | Photocopier | 1 | 6000 | 4320.9236 | Post Qualification | Prior | Plan
Actual
|  |  | Computers Printers | 1 | 3000 | 2160.4618 | Post Qualification | Prior | Plan
Actual
|  |  | Internet Connection | 1 | 200 | 144.0308 | Post Qualification | Prior | Plan
Actual
|  |  | Publicity Materials (USB, Keys, Notepads, Pens) | 0 |  |  | Post Qualification | Prior | Plan
Actual
|  |  | Banners | 0 |  |  | Post Qualification | Prior | Plan
Actual
|  |  | Interpretation Equipment | 0 |  |  | Post Qualification | Prior | Plan
Actual
|  |  | Bus | 0 |  |  | Post Qualification | Prior | Plan
Actual
|  |  | Car | 3 | 8640 | 6222.13 | Post Qualification | Prior | Plan
Actual
18 | 18 | Mutual Evaluation of Comoros (On-site visit and Face-to-Face Meeting) | Conference Hall | 0 |  |  | Post Qualification | Prior | Plan
Actual
|  |  | Secretariat Room | 1 | 0 | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Tea Break | 10 | 0 | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Photocopier | 1 | 0 | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Computers | 1 | 0 | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Printer | 1 | 0 | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Publicity Materials (USB, Keys, Notepads, Pens) | 0 |  |  | Post Qualification | Prior | Plan
Actual
|  |  | Banners | 0 |  |  | Post Qualification | Prior | Plan
Actual
|  |  | Interpretation Equipment | 0 |  |  | Post Qualification | Prior | Plan
Actual
|  |  | Bus | 0 |  |  | Post Qualification | Prior | Plan
Actual
|  |  | Car | 3 | 0 | 0 | Post Qualification | Prior | Plan
Actual
19 | 5 | Mutual Evaluation of Nigeria (on-site visit) - Completion | Conference Hall | 0 |  |  | Post Qualification | Prior | Plan
Actual
|  |  | Secretariat Room | 1 | 3500 | 2520.5388 | Post Qualification | Prior | Plan
Actual
|  |  | Tea Break | 10 | 2100 |  | Post Qualification | Prior | Plan
Actual
|  |  | Photocopier | 1 | 1500 | 1080.2309 | Post Qualification | Prior | Plan
Actual
|  |  | Computers | 1 | 375 | 270.0577 | Post Qualification | Prior | Plan
Actual
|  |  | Printer | 1 | 375 | 270.0577 | Post Qualification | Prior | Plan
Actual
|  |  | Publicity Materials (USB, Keys, Notepads, Pens) | 0 |  |  | Post Qualification | Prior | Plan
Actual
|  |  | Banners | 0 |  |  | Post Qualification | Prior | Plan
Actual
|  |  | Interpretation Equipment | 0 |  |  | Post Qualification | Prior | Plan
Actual
|  |  | Bus | 0 |  |  | Post Qualification | Prior | Plan
Actual
|  |  | Car | 2 | 1446 | 1041.3426 | Post Qualification | Prior | Plan
Actual
20 | 2 | ANNUAL REGIONAL FORUM OF HEADS OF FIU - (2 per year) | Conference Hall | 1 | 2000 | 1440.3079 | Post Qualification | Prior | Plan
Actual
|  |  | Secretariat Room | 1 | 1000 | 720.1539 | Post Qualification | Prior | Plan
Actual
|  |  | Tea Break | 24 | 1440 | 1037.0217 | Post Qualification | Prior | Plan
Actual
|  |  | Photocopier | 1 | 0 | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Computers | 1 | 0 | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Printer | 1 | 0 | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Publicity Materials (USB, Keys, Notepads, Pens) | 0 |  |  | Post Qualification | Prior | Plan
Actual
|  |  | Banners | 0 |  |  | Post Qualification | Prior | Plan
Actual
|  |  | Interpretation Equipment | 1 | 1400 | 1008.2155 | Post Qualification | Prior | Plan
Actual
|  |  | Bus | 0 |  |  | Post Qualification | Prior | Plan
Actual
|  |  | Car | 2 | 0 | 0 | Post Qualification | Prior | Plan
Actual
21 | 4 | Regional Hybrid Training Workshop on Asset Recovery for GIABA Member States (Anglophone and Francophone/Lusophone) | Conference Hall | 1 | 9200 | 6625.4162 | Post Qualification | Prior | Plan
Actual
|  |  | Secretariat Room | 1 | 2500 | 1800.3849 | Post Qualification | Prior | Plan
Actual
|  |  | Tea Break | 70 | 8400 | 6049.2931 | Post Qualification | Prior | Plan
Actual
|  |  | Photocopier | 1 | 1200 | 864.1847 | Post Qualification | Prior | Plan
Actual
|  |  | Computers | 3 | 1800 | 1296.2771 | Post Qualification | Prior | Plan
Actual
|  |  | Printer | 1 | 600 | 432.0924 | Post Qualification | Prior | Plan
Actual
|  |  | Publicity Materials (USB, Keys, Notepads, Pens, Banners) | 50 | 2500 | 1800.3849 | Post Qualification | Prior | Plan
Actual
|  |  | Internet Connection | 1 | 200 | 144.0308 | Post Qualification | Prior | Plan
Actual
|  |  | Interpretation Equipment | 1 | 2000 | 1440.3079 | Post Qualification | Prior | Plan
Actual
|  |  | Bus | 1 | 900 | 648.1385 | Post Qualification | Prior | Plan
Actual
|  |  | Car | 2 | 0 | 0 | Post Qualification | Prior | Plan
Actual
22 | 3 | Joint ECOWAS/Court of Justice/GIABA Regional Capacity building workshop on the Adjudication Economic and Financial Crimes cases for Judges | Conference Hall | 1 | 10500 | 7561.6164 | Post Qualification | Prior | Plan
Actual
|  |  | Secretariat Room | 1 | 4000 | 2880.6158 | Post Qualification | Prior | Plan
Actual
|  |  | Tea Break | 51 | 13770 | 9916.5198 | Post Qualification | Prior | Plan
Actual
|  |  | Photocopier | 1 | 900 | 648.1385 | Post Qualification | Prior | Plan
Actual
|  |  | Computers | 3 | 1350 | 972.2078 | Post Qualification | Prior | Plan
Actual
|  |  | Internet Connection | 1 | 3000 | 2160.4618 | Post Qualification | Prior | Plan
Actual
|  |  | Publicity Materials (USB, Keys, Notepads, Pens) | 0 |  |  | Post Qualification | Prior | Plan
Actual
|  |  | Banners | 0 |  |  | Post Qualification | Prior | Plan
Actual
|  |  | Interpretation Equipment | 1 | 2100 | 1512.3233 | Post Qualification | Prior | Plan
Actual
|  |  | Bus | 1 | 3250 |  | Post Qualification | Prior | Plan
Actual
|  |  | Car | 2 | 0 | 0 | Post Qualification | Prior | Plan
Actual
23 | 4 | Meeting of the GIABA Evaluation and Compliance Group (ECG) on MS Follow Up Reports (2 per year) | Conference Hall | 1 | 6400 | 4608.9852 | Post Qualification | Prior | Plan
Actual
|  |  | Secretariat Room | 1 | 2400 | 1728.3695 | Post Qualification | Prior | Plan
Actual
|  |  | Tea Break | 51 | 8160 | 5876.4562 | Post Qualification | Prior | Plan
Actual
|  |  | Photocopier | 1 | 0 | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Computers | 1 | 0 | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Printer | 1 |  |  | Post Qualification | Prior | Plan
Actual
|  |  | Publicity Materials (USB, Keys, Notepads, Pens) | 108 | 0 | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Banners | 2 | 0 | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Interpretation Equipment | 0 | 4000 | 2880.6158 | Post Qualification | Prior | Plan
Actual
|  |  | Bus | 0 |  |  | Post Qualification | Prior | Plan
Actual
|  |  | Car | 0 |  |  | Post Qualification | Prior | Plan
Actual
24 | 5 | GIABA Assessors Training and MER Report Writing | Conference Hall | 1 | 10000 | 7201.5394 | Post Qualification | Prior | Plan
Actual
|  |  | Secretariat Room | 3 | 14400 | 10370.2167 | Post Qualification | Prior | Plan
Actual
|  |  | Tea Break | 78 | 15600 | 11234.4015 | Post Qualification | Prior | Plan
Actual
|  |  | Photocopier | 1 | 1500 | 1080.2309 | Post Qualification | Prior | Plan
Actual
|  |  | Computers | 1 | 2250 | 1620.3464 | Post Qualification | Prior | Plan
Actual
|  |  | Internet Connection | 1 | 200 | 144.0308 | Post Qualification | Prior | Plan
Actual
|  |  | Publicity Materials (USB, Keys, Notepads, Pens,Banners) | 108 | 5000 | 3600.7697 | Post Qualification | Prior | Plan
Actual
|  |  | Banners | 55 | 1650 | 1188.254 | Post Qualification | Prior | Plan
Actual
|  |  | Interpretation Equipment | 2 | 7000 | 5041.0776 | Post Qualification | Prior | Plan
Actual
|  |  | Bus | 2 | 2100 | 1512.3233 | Post Qualification | Prior | Plan
Actual
|  |  | Car | 0 |  | 0 | Post Qualification | Prior | Plan
Actual
25 | 5 | GIABA Regional Training on FATF Standards and Methodology | Conference Hall | 1 | 2000 | 1440.3079 | Post Qualification | Prior | Plan
Actual
|  |  | Secretariat Room | 3 | 12600 | 9073.9396 | Post Qualification | Prior | Plan
Actual
|  |  | Tea Break | 68 | 13600 | 9794.0936
|  |  | Photocopier | 1 | 1500 | 1080.2309 | Post Qualification | Prior | Plan
Actual
|  |  | Computers | 1 | 2250 | 1620.3464 | Post Qualification | Prior | Plan
Actual
|  |  | Internet Connection | 1 | 200 | 144.0308 | Post Qualification | Prior | Plan
Actual
|  |  | Publicity Materials (USB, Keys, Notepads, Pens,Banners) | 55 | 1650 | 1188.254 | Post Qualification | Prior | Plan
Actual
|  |  | Banners | 2 | 0 | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Interpretation Equipment | 2 | 7000 | 5041.0776 | Post Qualification | Prior | Plan
Actual
|  |  | Bus | 2 | 2100 | 1512.3233 | Post Qualification | Prior | Plan
Actual
|  |  | Car | 0 |  |  | Post Qualification | Prior | Plan
Actual
26 | 4 | National Mutual Evaluation Pre-Assessment Training for MS and Preparation for ME (Guinea) | Conference Hall | 1 | 6000 | 4320.9236 | Post Qualification | Prior | Plan
Actual
|  |  | Secretariat Room | 1 | 2500 | 1800.3849 | Post Qualification | Prior | Plan
Actual
|  |  | Tea Break | 72 | 11520 | 8296.1734
|  |  | Photocopier | 1 | 1200 | 864.1847 | Post Qualification | Prior | Plan
Actual
|  |  | Computers Printer | 1 | 1200 | 864.1847 | Post Qualification | Prior | Plan
Actual
|  |  | Internet Connection | 1 | 200 | 144.0308 | Post Qualification | Prior | Plan
Actual
|  |  | Publicity Materials (USB, Keys, Notepads, Pens) | 60 | 0 | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Banners | 2 | 0 | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Interpretation Equipment | 0 | 2000 | 1440.3079 | Post Qualification | Prior | Plan
Actual
|  |  | Bus | 0 |  |  | Post Qualification | Prior | Plan
Actual
|  |  | Car | 2 | 1440 | 1037.0217 | Post Qualification | Prior | Plan
Actual
27 | 5 | Mutual Evaluation of The Gambia - (Face-to-Face Meeting) (Completion) | Conference Hall | 1 | 0 | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Secretariat Room | 1 | 3500 | 2520.5388 | Post Qualification | Prior | Plan
Actual
|  |  | Tea Break | 10 | 2100 | 1512.3233 | Post Qualification | Prior | Plan
Actual
|  |  | Photocopier | 1 | 1000 | 720.1539 | Post Qualification | Prior | Plan
Actual
|  |  | Computers Printers | 1 | 750 | 540.1155 | Post Qualification | Prior | Plan
Actual
|  |  | Internet connection | 1 | 300 | 216.0462 | Post Qualification | Prior | Plan
Actual
|  |  | Publicity Materials (USB, Keys, Notepads, Pens) | 56 | 0 | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Banners | 2 | 0 | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Interpretation Equipment | 0 |  |  | Post Qualification | Prior | Plan
Actual
|  |  | Bus | 2 | 0 |  | Post Qualification | Prior | Plan
Actual
|  |  | Car | 2 | 1680 | 1209.8586 | Post Qualification | Prior | Plan
Actual
28 | 24 | Mutual Evaluation of Liberia - (On-site visit and Face-to-Face Meeting) | Conference Hall | 0 |  | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Secretariat Room | 1 | 12000 | 8641.8473 | Post Qualification | Prior | Plan
Actual
|  |  | Photocopier | 1 | 4000 | 2880.6158 | Post Qualification | Prior | Plan
Actual
|  |  | Computers | 1 | 3000 | 2160.4618 | Post Qualification | Prior | Plan
Actual
|  |  | Tea break | 10 | 7200 | 5185.1084 | Post Qualification | Prior | Plan
Actual
|  |  | Publicity Materials (USB, Keys, Notepads, Pens) | 0 |  | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Internet connection | 1 | 300 | 216.0462 | Post Qualification | Prior | Plan
Actual
|  |  | Interpretation Equipment | 0 |  | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Bus | 0 |  | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Car | 2 | 5760 | 4148.0867 | Post Qualification | Prior | Plan
Actual
29 | 1 | National AML/CFT Media Outreach Activities | Conference Hall | 2 | 3000 | 2160.4618 | Post Qualification | Prior | Plan
Actual
|  |  | Secretariat Room | 2 | 1000 | 720.1539 | Post Qualification | Prior | Plan
Actual
|  |  | Tea Break | 30 | 2400 | 1728.3695 | Post Qualification | Prior | Plan
Actual
|  |  | Other communication/photos/videos | 4 | 800 | 576.1232 | Post Qualification | Prior | Plan
Actual
|  |  | Computers | 1 | 0 | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Printer | 1 | 0 | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Publicity Materials (USB, Keys, Notepads, Pens) | 35 | 1400 | 1008.2155 | Post Qualification | Prior | Plan
Actual
|  |  | Conference bags and gifts | 35 | 1400 | 1008.2155 | Post Qualification | Prior | Plan
Actual
|  |  | Interpretation Equipment | 3 | 3000 | 2160.4618 | Post Qualification | Prior | Plan
Actual
|  |  | Bus | 1 | 0 | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Car | 0 |  |  | Post Qualification | Prior | Plan
Actual
30 | 1 | Annual Ambassadors Briefing | Conference Hall | 1 | 2000 | 1440.3079 | Post Qualification | Prior | Plan
Actual
|  |  | Secretariat Room | 1 | 500 | 360.077 | Post Qualification | Prior | Plan
Actual
|  |  | Tea Break | 33 | 2640 | 1901.2064 | Post Qualification | Prior | Plan
Actual
|  |  | Photocopier | 1 | 450 | 324.0693 | Post Qualification | Prior | Plan
Actual
|  |  | Computers Printers | 1 | 450 | 324.0693 | Post Qualification | Prior | Plan
Actual
|  |  | Internet connection | 1 | 200 | 144.0308 | Post Qualification | Prior | Plan
Actual
|  |  | Publicity Materials (USB, Keys, Notepads, Pens, Banners) | 35 | 1750 | 1260.2694 | Post Qualification | Prior | Plan
Actual
|  |  | Conference bags and gifts | 33 | 1320 | 950.6032 | Post Qualification | Prior | Plan
Actual
|  |  | Interpretation Equipment | 3 | 3000 | 2160.4618 | Post Qualification | Prior | Plan
Actual
|  |  | Bus | 2 | 300 | 216.0462 | Post Qualification | Prior | Plan
Actual
|  |  | Other communication, Photos, Videos | 1 | 2300 | 1656.3541 | Post Qualification | Prior | Plan
Actual
31 | 3 | Regional Sensitization Workshop for CSOs on AML/CFT requirements | Conference Hall | 1 | 5400 | 3888.8313 | Post Qualification | Prior | Plan
Actual
|  |  | Secretariat Room | 1 | 1350 | 972.2078 | Post Qualification | Prior | Plan
Actual
|  |  | Tea Break | 35 | 8400 | 6049.2931 | Post Qualification | Prior | Plan
Actual
|  |  | Photocopier | 1 | 900 | 648.1385 | Post Qualification | Prior | Plan
Actual
|  |  | Computers | 1 | 450 | 324.0693 | Post Qualification | Prior | Plan
Actual
|  |  | Printer | 1 | 450 | 324.0693 | Post Qualification | Prior | Plan
Actual
|  |  | Publicity Materials (USB, Keys, Notepads, Pens) | 61 | 1325 | 954.204 | Post Qualification | Prior | Plan
Actual
|  |  | Internet connection | 1 | 200 | 144.0308 | Post Qualification | Prior | Plan
Actual
|  |  | Interpretation Equipment | 0 | 1500 | 1080.2309 | Post Qualification | Prior | Plan
Actual
|  |  | Bus | 2 | 150 | 108.0231 | Post Qualification | Prior | Plan
Actual
|  |  | Other communication Phto Video | 13 | 900 | 648.1385 | Post Qualification | Prior | Plan
Actual
32 | 3 | 2 Open House for Youths / National AML/CFT Awareness Raising Road Show for the General Public | Conference Hall | 1 | 8000 | 5761.2315 | Post Qualification | Prior | Plan
Actual
|  |  | Secretariat Room | 1 | 4000 | 2880.6158 | Post Qualification | Prior | Plan
Actual
|  |  | Tea Break | 270 | 43200 | 31110.6502 | Post Qualification | Prior | Plan
Actual
|  |  | Photocopier Printer Computer | 4 | 2400 | 1728.3695 | Post Qualification | Prior | Plan
Actual
|  |  | Other Communication (Video & Photos) | 5 | 1000 | 720.1539 | Post Qualification | Prior | Plan
Actual
|  |  | Internet Connection | 2 | 400 | 288.0616 | Post Qualification | Prior | Plan
Actual
|  |  | Publicity Materials (USB, Keys, Notepads, Pen,Banners) | 260 | 10400 | 7489.601 | Post Qualification | Prior | Plan
Actual
|  |  | Conference bags and gifts | 270 | 10800 | 7777.6626 | Post Qualification | Prior | Plan
Actual
|  |  | Interpretation Equipment | 1 | 1500 | 1080.2309 | Post Qualification | Prior | Plan
Actual
|  |  | Bus | 2 | 600 | 432.0924 | Post Qualification | Prior | Plan
Actual
|  |  | Car | 2 | 480 | 345.6739 | Post Qualification | Prior | Plan
Actual
33 | 3 | Regional Training for Journalists on Investigative Reporting of Economic Crimes in W/A | Conference Hall | 1 | 4410 | 3175.8789 | Post Qualification | Prior | Plan
Actual
|  |  | Secretariat Room | 1 | 1500 | 1080.2309 | Post Qualification | Prior | Plan
Actual
|  |  | Tea Break | 35 | 4200 | 3024.6465 | Post Qualification | Prior | Plan
Actual
|  |  | Photocopier | 1 | 900 | 648.1385 | Post Qualification | Prior | Plan
Actual
|  |  | Computers | 1 | 450 | 324.0693 | Post Qualification | Prior | Plan
Actual
|  |  | Printer | 1 | 450 | 324.0693 | Post Qualification | Prior | Plan
Actual
|  |  | Publicity Materials (USB, Keys, Notepads, Pens) | 0 | 0 | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Internet Connection | 1 | 150 | 108.0231 | Post Qualification | Prior | Plan
Actual
|  |  | Interpretation Equipment | 1 | 1500 | 1080.2309 | Post Qualification | Prior | Plan
Actual
|  |  | Bus | 2 | 300 | 216.0462 | Post Qualification | Prior | Plan
Actual
|  |  | Other Comuncation | 12 | 960 | 691.3478 | Post Qualification | Prior | Plan
Actual
34 | 3 | ECOWAS Day Celebrations | Conference Hall | 1 | 2000 | 1440.3079 | Post Qualification | Prior | Plan
Actual
|  |  | Secretariat Room | 1 | 4000 | 2880.6158 | Post Qualification | Prior | Plan
Actual
|  |  | Tea Break | 70 | 3500 | 2520.5388 | Post Qualification | Prior | Plan
Actual
|  |  | Photocopier | 1 | 1500 | 1080.2309 | Post Qualification | Prior | Plan
Actual
|  |  | Computers | 1 | 750 | 540.1155 | Post Qualification | Prior | Plan
Actual
|  |  | Printer | 1 | 750 | 540.1155 | Post Qualification | Prior | Plan
Actual
|  |  | Publicity Materials (USB, Keys, Notepads, Pens, Banners) | 4 | 300 | 216.0462 | Post Qualification | Prior | Plan
Actual
|  |  | Other Communication Photos Videos | 3 | 750 | 540.1155 | Post Qualification | Prior | Plan
Actual
|  |  | Interpretation Equipment | 1 | 500 | 360.077 | Post Qualification | Prior | Plan
Actual
|  |  | Bus | 3 | 0 | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Car | 0 |  | 0 | Post Qualification | Prior | Plan
Actual
|  | 5th National Lecture Series on AML/CFT Awareness in MS | Conference Hall | 1 | 2000 | 1440.3079 | Post Qualification | Prior | Plan
Actual
|  |  | Secretariat Room | 1 | 500 | 360.077 | Post Qualification | Prior | Plan
Actual
|  |  | Tea Break | 120 | 4800 | 3456.7389 | Post Qualification | Prior | Plan
Actual
|  |  | Photocopier Computer Printer | 1 | 600 | 432.0924 | Post Qualification | Prior | Plan
Actual
|  |  | Photo/Video/Photocopier |  |  | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Publicity Items (T Shirts and Caps) | 120 | 3600 | 2592.5542 | Post Qualification | Prior | Plan
Actual
|  |  | Publicity Materials (USB, Keys, Notepads, Pens, Banners) | 100 | 3000 | 2160.4618 | Post Qualification | Prior | Plan
Actual
|  |  | Debate Prizes (Gift Items) | 1 | 2500 | 1800.3849 | Post Qualification | Prior | Plan
Actual
|  |  | Interpretation Equipment |  |  | 0 | Post Qualification | Prior | Plan
Actual
|  |  | Bus | 2 | 200 | 144.0308 | Post Qualification | Prior | Plan
Actual
|  |  | Car Hire | 3 | 360 | 259.2554 | Post Qualification | Prior | Plan
Actual
|  |  | Other Communication | 9 | 900 | 648.1385 | Post Qualification | Prior | Plan
Actual
| 1 | 5th Inter-University Speech Contest on AML/CFT Impact of West African Economies | Conference Hall | 1 | 2000 | 1440.3079 | Post Qualification | Prior | Plan
Actual
|  |  | Secretariat Room | 1 | 500 | 360.077 | Post Qualification | Prior | Plan
Actual
|  |  | Tea Break | 150 | 6000 | 4320.9236 | Post Qualification | Prior | Plan
Actual
|  |  | Photocopier Computer Printer | 1 | 900 | 648.1385 | Post Qualification | Prior | Plan
Actual
|  |  | Photo/Video/Photocopier | 1 | 600 | 432.0924 | Post Qualification | Prior | Plan
Actual
|  |  | Publicity Items (T Shirts and Caps) | 150 | 6000 | 4320.9236 | Post Qualification | Prior | Plan
Actual
|  |  | Publicity Materials (USB, Keys, Notepads, Pens, Banners) | 100 | 3000 | 2160.4618 | Post Qualification | Prior | Plan
Actual
|  |  | Debate Prizes (Gift Items) | 1 | 2500 | 1800.3849 | Post Qualification | Prior | Plan
Actual
|  |  | Interpretation Equipment | 1 | 750 | 540.1155 | Post Qualification | Prior | Plan
Actual
|  |  | Bus | 2 | 300 | 216.0462 | Post Qualification | Prior | Plan
Actual
|  |  | Car Hire | 3 | 360 | 259.2554 | Post Qualification
|  |  | Other Communication | 2 | 200 | 144.0308 | Post Qualification | Prior | Plan
Actual
35 | 3 | Annual World Press Conference/Presentation of 2021 Annual Report | Conference Hall | 1 | 1000 | 720.1539 | Post Qualification | Prior | Plan
Actual
|  |  | Secretariat Room | 1 | 500 | 360.077 | Post Qualification | Prior | Plan
Actual
|  |  | Tea Break | 30 | 2400 | 1728.3695 | Post Qualification | Prior | Plan
Actual
|  |  | Photocopier | 1 | 300 | 216.0462 | Post Qualification | Prior | Plan
Actual
|  |  | Computers | 1 | 150 | 108.0231 | Post Qualification | Prior | Plan
Actual
|  |  | Printer | 1 | 150 | 108.0231 | Post Qualification | Prior | Plan
Actual
|  |  | Publicity Materials (USB, Keys, Notepads, Pens, Banners) | 30 | 1500 | 1080.2309 | Post Qualification | Prior | Plan
Actual
|  |  | Internet Connection | 1 | 200 | 144.0308 | Post Qualification | Prior | Plan
Actual
|  |  | Interpretation Equipment | 1 | 500 | 360.077 | Post Qualification | Prior | Plan
Actual
|  |  | Bus | 2 | 300 | 216.0462 | Post Qualification | Prior | Plan
Actual
|  |  | Other Communication | 9 | 100 | 72.0154 | Post Qualification | Prior | Plan
Actual
36 | 2 | National Sensitization Seminar for Religious Leaders and Institutions on AML/CFT | Conference Hall | 2 | 8000 | 5761.2315 | Post Qualification | Prior | Plan
Actual
|  |  | Secretariat Room | 1 | 1000 | 720.1539 | Post Qualification | Prior | Plan
Actual
|  |  | Tea Break | 60 | 4800 | 3456.7389 | Post Qualification | Prior | Plan
Actual
|  |  | Photocopier | 1 | 600 | 432.0924 | Post Qualification | Prior | Plan
[5 empty] | 300 |  |  |  | Actual
|  |  | Computers | 1 | 300 | 216.0462 | Post Qualification | Prior | Plan
Actual
|  |  | Printer | 1 | 450 | 324.0693 | Post Qualification | Prior | Plan
Actual
|  |  | Publicity Materials (USB, Keys, Notepads, Pens,Banners) | 60 | 2400 | 1728.3695 | Post Qualification | Prior | Plan
Actual
|  |  | Photographs and Video / Projectors | 2 | 960 | 691.3478 | Post Qualification | Prior | Plan
Actual
|  |  | Interpretation Equipment | 1 | 1000 | 720.1539 | Post Qualification | Prior | Plan
Actual
|  |  | Bus | 2 | 600 | 432.0924 | Post Qualification | Prior | Plan
Actual
|  |  | Car | 3 | 720 | 518.5108 | Post Qualification | Prior | Plan
Actual
| 1 | Support to Journalist/CSO Networks on AML/CFT in West Africa (LIC + AIC) | GRANT | 5 | 60000 | 43209.2364 | Post Qualification | Prior | Plan
Actual
|  | TOTAL |  |  | 1205658.12 | 874873.1217
|  | LCB: Local Competitive Bidding (2 months) |  |  | Exchange Rate
|  | RCB:Open Regional Competitive Bidding (3 months) |  |  | 1UA =
IRCB: International Restrictive Competitive Bidding (2 months)
|  | ICB:Open International Competitive Bidding (3 months) |  |  | * les dates des activités n'ont pas encore été finalisé par les chargés de programmes
RFQ: Request For Quotation (1 month)
DC: Direct Contracting (1 month)
RT: Regional Restrictive Tender (2 months)
NA : Not Applicable

## Works
| PROCUREMENT PLAN 2020 - WORKS | Basic Data | [6 empty] | Implementation |  | Duration
S/N | Description | Lot No. | Estimated Budget USD | Estimated Budget UA | Procurement Method | Pre / Post Qualification | Prior or Post Review | Plan vs. Actual | Start Date (of the Procurement Process) | End Date (of the Procurement process in line with Procurement deadline set up in the Code) | Total Duration
| List of Contracts | [6 empty] | Plan-Actual
1 |  |  |  | 0 |  | Post Qualification | Prior | Plan
Actual
2 | [5 empty] | Post Qualification | Prior | Plan
Actual
3 | [5 empty] | Post Qualification | Prior | Plan
Actual
TOTAL
| LCB: Local Competitive Bidding (2 months) |  | Exchange Rate
| RCB:Open Regional Competitive Bidding (3 months) |  | 1UA =
IRCB: International Restrictive Competitive Bidding (2 months)
ICB:Open International Competitive Bidding (3 months)
RFQ: Request For Quotation (1 month)
DC: Direct Contracting (1 month)
RT: Regional Restrictive Tender (2 months)