## Consultancy
| PROCUREMENT PLAN 2022 ECOWAS AGENCIES - CONSULTANCY |  | Basic data | [5 empty] | Impementation |  | Duration
S/N | Description | Bid Reference | Selection Method | Lump Sum / Time Based | Estimated Budget USD | Estimated Budget UA | Prior/ Post Review | Plan vs. Actual | Start Date(of the Procurement Process) | End Date (of the procurement process in line with Procurement deadline set up in the Code) | Total Duration of the Procurement Process including delivery
List of Contract
PPDU
1 | Study on Amilcar Cabral Submarine Cable Project |  | QCBS | Lumpsum | 751233 | 522135 | Prior | PLAN | Nov 2021 | April 2022 | 12 months ( 4 months process and 8 month assignment )
Actual
2 | Update on Macro- Economic Component of FODETE Study |  | DC (QCBS) | Lumpsum | 80130 | 55694 | Prior | PLAN | February 2022 | June 2022 | 7 months ( 4 months process and 3 month assignment )
|  |  |  | Lumpsum |  |  |  | Actual
3 | Feasibility Study on Bamako - Ouangoulodou Railway Project |  | QCBS | Lumpsum | 186973 | 129954 | Prior | PLAN | April 2022 | July 2022 | 12 months ( 4 months process and 8 month assignment )
|  |  |  | Lumpsum |  |  |  | Actual
4 | Consultancy for Video Documentary on Infrastructure Masterplan |  | QCBS | Lumpsum | 71938 | 50000 | Prior | PLAN | March 2022 | July 2022 | 8 months ( 4 months process and 4 month assignment )
|  |  |  | Lumpsum |  |  |  | Actual
5 | Update on PPDU Business Plan |  | QCBS | Lumpsum | 45073 | 31328 | Prior | PLAN | June 2022 | October 2022 | 7 months ( 4 months process and 3 month assignment )
|  |  |  | Lumpsum |  |  |  | Actual
6 | Audit on FODETE Special Account |  | DC/CP | Lumsum | 20000 | 13908 | Prior | PLAN | April 2022 | May 2022 | 2 month (one month process and one month assignment)
Actual
6 | Recruitment of Short term Experts (Communication, Gender, Sustianable Development, Capacity Building Expert, Expenditure verification etc) |  | ICS | Lumpsum | 96512.3035 | 69503.7157 | Prior | PLAN | April 2022 | June 2022 | 2 months process and 1 year contract
|  |  |  | Lumpsum |  |  |  | Actual
7 | Mid - term Evaluation of AECID MOU |  | ICS | Lumpsum | 40499.9936 | 29166.23 | Post | PLAN | June 2022 | August 2022 | 4 months (2 months process and 2 months assignment)
|  |  |  | Lumpsum |  |  |  | Actual
| TOTAL |  |  |  | 1292359.2972 | 901688.9457
| NA: Not Applicable |  | Exchange Rate
| CQ: Consultant Qualifications - (2 months) |  | 1UA = 1.438772
ICS: Selection of Individual Consultant (2 months)
QCBS: Quality Cost Based Selection (4 months)
DC: Direct Contracting (2 months)
LCS: Least Cost Selection (4 months)
CP: Call for Proposals

## Goods
| PROCUREMENT PLAN 2022 ECOWAS AGENCIES - GOODS | Basic data | [6 empty] | Implementation |  | Duration
S/N | Description | Lot No. | Estimated Buget USD | Estimated Budget UA | Procurement Method | Pre/Post Qualification | Prior/ Post Review | Plan vs. Actual | Start Date | End Date | Total Duration
List of Contracts
| PPDU | [6 empty] | Plan-Actual
1 | Purchase IT - Equipment (Laptops, Desktops, Scanners, Photocopiers, incl. IT Consumables) | 1 | 31339 | 21781.7695 | RFQ | Post Qualification | Post | Plan | March 2022 | April 2022 | 1 month
Actual
2 | Purchase of Office furniture | 1 | 9099 | 6324.1431 | RFQ | Post Qualification | Post | Plan | March 2022 | April 2022 | 1 month
Actual
3 | Purchase of Computer consommables | 1 | 10199 | 7088.684 | RFQ | Post Qualification | Post | Plan | March 2022 | April 2022 | 1 month
Actual
4 | Purchase Office and consumable supplies | 1 | 3600 | 2502.1338 | RFQ | Post Qualification | Post | Plan | Februray 2022 | March 2022 | 1 month
Actual
5 | Purchase Diary and key holders | 1 | 12000 | 8340.4459 | RFQ | Post Qualification | Post | Plan | July 2022 | August 2022 | 1 month
Actual
6 | Purchase GIS Mapping fees | 1 | 3000 | 2085.1115 | DC | Post Qualification | Post | Plan | February 2022 | March 2022 | 1 month
Actual
7 | Purchase Vehicles | 1 | 64411 | 44768.0383 | LCB | Post Qualification | Post | Plan | April 2022 | May 2022 | 2 month
Actual
| TOTAL |  | 69237 | 92890.3259
| LCB: Local Competitive Bidding (2 months) |  | Exchange Rate
| RCB: Regional Competitive Bidding (2.5 months) |  | 1UA = 1.438772
IRCB: International Restrictive Competitive Bidding (2 months)
ICB: International Competitive Bidding (2.5 months)
RFQ: Request For Quotation (1 month)
DC: Direct Contracting (1 month)
RT: Restrictive Tender (2 months)
NA : Not Applicable

## Works
| PROCUREMENT PLAN 2019 ECOWAS AGENCIES - WORKS | Basic Data | [6 empty] | Implementation |  | Duration
S/N | Description | Lot No. | Estimated Budget USD | Estimated Budget UA | Procurement Method | Pre / Post Qualification | Prior or Post Review | Plan vs. Actual | Start Date | End Date | Total Duration
| List of Contracts | [6 empty] | Plan-Actual
1 | [5 empty] | Post Qualification | Prior | Plan
Actual
2 | [5 empty] | Post Qualification | Prior | Plan
Actual
3 | [5 empty] | Post Qualification | Prior | Plan
Actual
4 | [5 empty] | Post Qualification | Prior | Plan
Actual
5 | [5 empty] | Post Qualification | Prior | Plan
Actual
TOTAL
| RFQ: Request for Quotation (1 month) |  | Exchange Rate
| LCB: LOCAL Competitive Bidding (2 months) |  | 1UA = 1.438772
ICB: International Competitive Bidding (2.5 months)
RT: Restrictive Tender (2 months)
NA: NOT APPLICABLE